## Sheet1
2017 Program of Work
Date Completed | New or On-going Intiative | Initiative or Activity | Person Responsible | Progress
| New | Create partnership with Alumni Assoc, if warranted |  | President, Past President, and President-elect will meet with Alumni staff in February
| New | Develop new brochure | Newsletter Committee-Jeff Keown, contact person | Contract approved, work has begun
January, 2017 | New | Revision of operating procedures, reflecting changes in the association | John Comer, Jim Griesen, Board | completed
| New and on-going | Invite retirees to join the association | Board and all members | Approximately ten new members have been approved. This will be on-going
| New and on-going | Clarify benefits for emeriti and retirees, primarily because of new membership category | Doug Zatechka, Benefits Chair and Board | Progress has been made. Board members are clarifying remaining items
January, 2017 | New | Complete Big Ten Conference Report | Jim Griesen, Jack Goebel and all Board members | completed
| New | Investigate current service given by members to (1) the university and (2) community. Development of a survey for this purpose | Ad hoc committee--John Comer, Jim Griesen, Roger Kirby, Doug Zatechka, John Bernthal, and Doug Jose
February, 2017 | New | Investigate Wisherd fund and its availability for all members because of new membership structure | Jim Griesen, Julie Johnson, Rita Kean | completed
| New | Investigate awards given by other Big Ten Institutions | Al Seagren and Pat Crews, Awards co-chairs
| New | Establish new awards for association, where appropriate | Al Seagren and Pat Crews, Awards co-chairs
January, 2017 | New | Purchase a new camera for oral history project | Doug Jose | purchased
| Ongoing | Publish two newsletters (spring and fall) | Newsletter Committee-Doug Jose, chair | Spring newsletter completed
| Ongoing | Implement six luncheon/meetings with speakers of interest | Rita Kean, president-elect | All luncheons have been planned for spring semester. October has been planned.
| Ongoing | Implement a spring and fall tour for member participation | Kay Rockwell, Member Relations chair | tour possibilities have been identified. Great Plains Museum is completed
| Ongoing | Implement coffee house chats and social events for members | Rita & Don Weeks, liaisons | one event was held; others are being planned
January, 2017 | Ongoing | Develop a budget and financial reports | Jack Goebel, Julie Johnson, Jim Griesen, Rita Kean and Board members | completed
| Ongoing | Update website | John Comer, Website chair | continual process, letter from the president has been posted